## Sheet1
PROJECT LIST
Drawing No | Type of equipment | PO Date | Del. Date | Quantity | TAG No | Job Description
RDT 21-01 |  |  |  | 4
RDT 21-02
RDT 21-03
RDT 21-04
RDT 21-05
DEPARTMENTS | Design
DESIGN DEPT.
Sr No | Task | Responsible | Target Date | Planned Date | Send For Approval | Release Date | Revision no
1 | Fabrication Drawing
2 | Drawing sent to client Approval
3 | POS as per code
4 | Bill of materail
5 | vendor drawing
6 | Name plate drawing
7 | Plate Layout
8 | CNC program
9 | RT sketch
10 | Welding Sketch
11 | Asbuilt Drawing
12 | Transport Layout
PURCHASE DEPT.
BOM
SR.NO | Description | Materail Specification | Size | Qty | Available Stock | To be Procured | Req. Date For Production | PO Released Date | Expected Del Date | Actual Rec. date | Material TC required | TC Received
1
2
3
PRODUCTION DEPT
SR.No | Activity | Plan Date | End Date | Actual Start Date | Complection Date | Man Power Category | Inspection By Production | REWORK | Inspection By QC | TPI Call | Inspection By TPI | COST | RCA DONE
TASK 1 | MATERIAL
1 | Shell Plate
2 | Dish Plate
3 | Nozzle Flange
4 | Nozzle Pipe
5 | Paint
TASK 2 | DISHEND MAKING
1 | Plate Marking
2 | Cutting
3 | To Vendor
4 | Bending
5 | Inspection At Vendor End
6 | From Vendor
7 | Ready Dishend Received At Shop
8 | Dish Bevelling
TASK 3 | SHELL MAKING
1 | Shell Plate Marking
2 | Shell Plate Cutting
3 | Shell Plate Pre Punching
4 | Plate Rolling
5 | L-Seam Setup
6 | Inspection
7 | L-Seam Welding
8 | Re-Rolling
9 | RT (IF REQUIRED)
TASK 4 | Pipe To Flange Setup
1 | Pipe Cutting
2 | Pipe Bevelling
3 | Pipe To Flange Setup
4 | Welding
5 | RT (IF REQUIRED)
TASK 5 | LIFITING LUG MAKING
1 | Marking
2 | Cutting
3 | Setup
4 | Welding
5 | Grinding/Finishing
TASK 6 | Fabrication Activity
1 | C- Seam fittup (Shell To Dish 1 Nos)
2 | Welding
3 | Inside Grinding
4 | Nozzle Marking
5 | Inspection
6 | Nozzle Cutting
7 | V -Preparation
8 | Nozzle Setup
9 | Inspection
10 | Welding
11 | Inside Grinding
12 | Inside Painting
13 | Skirt Setup
14 | Welding
15 | 2nd Dish To Skirt Fitup
16 | Welding
17 | Inside Grinding
18 | Inside Painting
19 | 2nd Dish to shell setup
20 | welding
21 | LL, Saddle,Name plate fitup
22 | Welding
23 | finishing
24 | Final Dimension Check and Visual Inspection
25 | Pneumatic test
26 | Hydrotest
27 | Surface preparation and Painting
28 | Dispatch
VENDOR OUTSOURSED JOBS
Drawing no | Description | Vendor name | Material sent date | Planned Accepted date | Actual Recivied Date | Resaon For Dealy
RADIOGRAPHY
JOB NO | RT OFFER | RESULT | REMARk
PRE-DISPATCH
JOB NO | Actual | Inspection By production | Inspection by QC | Spare list | Transport saddle
DOSSIER
JOB NO | Planned | Actual
CLIENT APPROVAL FOR DEVIATION
SR.NO | Request By | Deviation Details | RCD Approval | Released To Production