## RECIVIER
RECEIVER
MATERAIL RECEIVING PROCESS
Plate Recivied At Shop
Plates Unloading
After Materail recivied check as per challan (Size & QTY.)
Check Challan As per PO
As Per Challan Fill up the GRN
Recored & Check the HEAT NUMBER ,PLATE NUMBER Afetr Give To QC DEPT.
Matrail Size Give To Design DEPT.
Layout Taken from Design DEPT.
PARALLEL ACTIVITY | DISHEND MAKING | SHELL MAKING | Pipe To Flange Setup | LIFITING LUG MAKING | MANHOLE ASSLY | Skirt Assly.
DISH | Plate Marking | Shell Plate Marking | Pipe Cutting | Marking | Manhole plate cutting | Skirt Shell Rolling
BOTTOM SKIRT | Cutting | Shell Plate Cutting | Pipe Bevelling | Cutting | Rolling | L Seam Welding
PIPE TO FLANGE | To Vendor | Shell Plate Pre Punching | Pipe To Flange Setup | Setup | L Seam Welding | Re-Rolling
MANHOLE ASSLY. | Bending | Plate Rolling | Welding | Welding | Grinding | Skirt Opening
LIFTING LUG ASSLY. | Inspection At Vendor End | L-Seam Setup | RT (IF REQUIRED) | Grinding/Finishing | Bending | Gusset Setup
Shell Making | From Vendor | Inspection |  |  |  | Welding
| Ready Dishend Received At Shop | L-Seam Welding |  |  |  | Finishing
| Dish Bevelling | Re-Rolling
RT (IF REQUIRED)
Fabrication Activity
C- Seam fittup (Shell To Dish 1 Nos)
Welding
Inside Grinding
Nozzle Marking
Inspection
Nozzle Cutting
V -Preparation
Nozzle Setup
Inspection
Welding
Inside Grinding
Inside Painting
Skirt Setup
inspection
Welding
2nd Dish To Skirt Fitup
Welding
LL, Saddle,Name plate fitup
Welding
finishing
Final Dimension Check and Visual Inspection
Pneumatic test
Hydrotest
Surface preparation and Painting
inspection
Dispatch

## COLUMN
COLUMN
MATERAIL RECEIVING PROCESS
Plate Recivied At Shop
Plates Unloading
After Materail recivied check as per challan (Size & QTY.)
Check Challan As per PO
As Per Challan Fill up the GRN
Recored & Check the HEAT NUMBER ,PLATE NUMBER Afetr Give To QC DEPT.
Matrail Size Give To Design DEPT.
Layout Taken from Design DEPT.
PARALLEL ACTIVITY | DISHEND MAKING | STIFFNER MAKING | BODY FLANGE | SHELL MAKING | PIPE TO FLANGE FITUP | LIFITING LUG MAKING | SADDLE BASE PLATE | SIGHT GLASS | RF PAD
DISH | Plate Marking | Plate Marking | Plate Cutting | Shell Plate Marking | Pipe Cutting | Marking | Plate Marking & Cutting | Plate Marking | Marking
BodyFlange | Cutting | Cutting | Segment Bevelling Or Plate Bending | Shell Plate Cutting | Pipe Bevelling | Cutting | Saddle Assly. | Plate Cutting | Cutting
Stiffner Bending | To Vendor | To Vendor | Segment Fitup | Plate Bevelling | Pipe To Flange Setup | Setup | Saddle Welding | Plate M/C | Grinding
Saddle Making | Bending | Bending | Body Flange segment welding | Pre-punching | Welding | Welding |  | Plate M/C & Drilling
LL Making | Inspection At Vendor End | Inspection At Vendor End | Straightening | Rolling | RT (IF REQUIRED) | Grinding/Finishing |  | Tapping
Pipe To Flange | From Vendor | From Vendor | Grinding/Finishing | L-Seam Fitup
Slight Glass | Ready Dishend Received At Shop | Ready Stiffner Received At Shop | RT/UT (IF REQUIRED) | Plate L-seam welding
RF Pad | Dish Bevelling |  | Machining | Inside Grinding/Finishing
|  |  | Drilling | Re-Rolling
Liner Fitup (IF REQUIRED)
|  |  | Liner Welding |  | Fabrication Activity
|  |  | Machining |  | C-seam Fitup
Inspection
Welding
Inside Grinding/Finishing
Inspection
Body Flange to shell Fitup
Pre-Alligment
Inspection
Body Flange Welding
Grinding/Finishing
Nozzle marking
Inspection
Profile Cutting/Grinding
Nozzle Fitup
Inspection
Nozzle welding
Inside Back-chip Grinding
Welding
Dummy Passing
External & Internals Fitup (Packing Rings, Channel Shell, Support Channel)
Internal Welding
Inspection
Acid Cleaning
RF Pad & Body Flange Liner Pneumatic
Final Dimension Check and Visual Inspection
Final Allignment
inspection
Hydrotest
inspection
Painting
inspection
Dispatch

## TANK
TANK
MATERAIL RECEIVING PROCESS
Plate Recivied At Shop
Plates Unloading
After Materail recivied check as per challan (Size & QTY.)
Check Challan As per PO
As Per Challan Fill up the GRN
Recored & Check the HEAT NUMBER ,PLATE NUMBER Afetr Give To QC DEPT.
Matrail Size Give To Design DEPT.
Layout Taken from Design DEPT.
PARALLEL ACTIVITY | DISHEND MAKING | Top CONE MAKING | COIL MAKING | SHELL MAKING | Pipe To Flange Setup | LIFITING LUG MAKING | MANHOLE ASSLY | SADDLE BASE PLATE | SIGHT GLASS | RF PAD
DISH | Plate Marking | Plate Marking | Plate Marking | Shell Plate Marking | Pipe Cutting | Marking | Manhole plate cutting | Plate Marking & Cutting | Plate Marking | Marking
Saddle support | Cutting | Cutting | Cutting | Shell Plate Cutting | Pipe Bevelling | Cutting | Rolling | Saddle Assly. | Plate Cutting | Cutting
PIPE TO FLANGE | To Vendor | To Vendor | To Vendor | Shell Plate Pre Punching | Pipe To Flange Setup | Setup | L Seam Welding | Saddle Welding | Plate M/C | Grinding
MANHOLE ASSLY. | Bending | Bending | Bending | Plate Rolling | Welding | Welding | Grinding |  | Plate M/C & Drilling
LIFTING LUG ASSLY. | Inspection At Vendor End | Inspection At Vendor End | Inspection At Vendor End | L-Seam Setup | RT (IF REQUIRED) | Grinding/Finishing | Davit Assly |  | Tapping
Shell Making | From Vendor | From Vendor | From Vendor | Inspection |  |  | Welding
Coil bending | Ready Dishend Received At Shop | Ready Cone Received At Shop | Ready c Received At Shop | L-Seam Welding
Sight Glass | Dish Bevelling | L Seam Welding | Dish Bevelling | Re-Rolling
RF Pad |  | inside grinding |  | RT (IF REQUIRED)
Top Cone |  | RT (if L seam)
|  | Cone Bevelling |  |  | Fabrication Activity (TANK WITH COIL)
C Seam Fitup
inspection
Welding
Grinding / Finishing
coil plate marking on shell & Bottom dish
inspection
coil fitup
welding
Nozzle marking
inspection
Profile Cutting/Grinding
Nozzle Fitup
inspection
Nozzle welding
Inside Back-chip Grinding
Welding
inspection
inside assly fitup
welding
2nd side dish/Cone setup
inspection
welding
inside back chip
welding
RT
saddle setup
welding
Finishing
Final Dimension Check and Visual Inspection
inspection
coil Pneumatic test
inspection
Shell Pneumatic test
inspection
Hydrotest
inspection
Surface preparation and Painting
Dispatch
Fabrication Activity (TANK WITH JACKET)
C Seam Fitup
inspection
Welding
Grinding / Finishing
Nozzle marking Jacket shell & main shell
inspection
Jacket shell insert & cone to shell setup
welding
inspection
Profile Cutting/Grinding
Nozzle Fitup
inspection
Nozzle welding
Inside Back-chip Grinding
Welding
inspection
inside assly fitup
welding
2nd side dish setup
inspection
welding
inside back chip
welding
RT
saddle setup
welding
Finishing
Final Dimension Check and Visual Inspection
inspection
coil Pneumatic test
inspection
Shell Pneumatic test
inspection
Hydrotest
inspection
Surface preparation and Painting
Dispatch

## HE CONDENSER
HEAT EXCHANGER CONDENSER
MATERAIL RECEIVING PROCESS
Plate Recivied At Shop
Plates Unloading
After Materail recivied check as per challan (Size & QTY.)
Check Challan As per PO
As Per Challan Fill up the GRN
Recored & Check the HEAT NUMBER ,PLATE NUMBER Afetr Give To QC DEPT.
Matrail Size Give To Design DEPT.
Layout Taken from Design DEPT.
PARALLEL ACTIVITY | BAFFLE MAKING | TUBESHEET MAKING | BELLOW MAKING | HEADER RHS /LHS | CONE MAKING | DISHEND MAKING | BODY FLANGE | SHELL MAKING | PIPE TO FLANGE FITUP | LIFITING LUG MAKING | RF PAD | N1 Nozzle
BAFFLE MAKING | Baffle Plate Marking / Cutting | Plate Marking | Plate Marking | Shell Plate Marking | Plate Marking | Plate Marking | Plate Cutting | Shell Plate Marking | Pipe Cutting | Marking | Marking | Sheel to cone setup
TUBESHEET MAKING | Drilling | Plate Cutting | Cutting | Shell Plate Cutting | Cutting | Cutting | Segment Bevelling Or Plate Bending | Shell Plate Cutting | Pipe Bevelling | Cutting | Cutting | welding
DISHEND MAKING | Machining | Machining | To Vendor | Shell Plate Pre Punching | To Vendor | To Vendor | Segment Fitup | Plate Bevelling | Pipe To Flange Setup | Setup | Grinding | cone to shell setup
BODY FLANGE | Tie Rod Spacer Cutting | Hole Marking | Bending | Plate Rolling | Bending | Bending | Body Flange segment welding | Pre-punching | Welding | Welding |  | welding
SHELL MAKING | Skeltan Making | Drilling | From Vendor | L-Seam Setup | Inspection At Vendor End | Inspection At Vendor End | Straightening | Rolling | RT (IF REQUIRED) | Grinding/Finishing |  | body flange setup
PIPE TO FLANGE FITUP | Bunddle Making | Slot Marking | Inside ID cutting | L-Seam Welding | From Vendor | From Vendor | Grinding/Finishing | L-Seam Fitup |  |  |  | welding
LIFITING LUG MAKING | Fitup external plate fitup on bundle(if given in drawing) | Grooving | To Vendor | Re-Rolling | Ready Cone Received At Shop | Ready Dishend Received At Shop | RT/UT (IF REQUIRED) | Plate L-seam welding |  |  |  | nozzle marking
RF PAD | welding |  | Bending | Shell To Dish/Body Flange fitup | L Seam Welding | Dish Bevelling | Machining | Inside Grinding/Finishing |  |  |  | cutting & v prepraction
BELLOW | finishing |  | Ready Bellow Received At Shop | welding | inside grinding |  | Drilling | Re-Rolling |  |  |  | nozzle setup
HEADER |  |  | Bellow Bevelling | Nozzle marking & cutting | RT |  | Liner Fitup (IF REQUIRED) |  |  |  |  | welding
CONE |  |  |  | Nozzle setup | Cone Bevelling |  | Liner Welding |  |  |  |  | inside grinding
|  |  |  | Nozzle welding |  |  | Machining |  |  |  |  | welding
|  |  |  | Finishing | [7 empty] | finishing
Fabrication Activity
C-seam Fitup (Shell Or Bellow)
Welding
Inside Grinding/Finishing
Nozzle marking
Profile Cutting/Grinding
Nozzle Fitup
Nozzle welding
Inside Back-chip Grinding
Internals Fitup (Partition plate,Vapour box,etc.)
Internal Welding
Skeleton making
Bundle making
Tube insert
Bundle insert
Tubesheet Fitup
welding
tube guide
welding
N1 nozzle fitup
welding
Tube Expansion
Outside Fitup
Welding
Finishing
Shell side Pneumtic Test
Shell Hydro Test
Tube side Pneumtic Test
Tube Hydro
Painting
Dispatch

## HE EVAPORATOR
HEAT EXCHANGER EVAPORATOR
MATERAIL RECEIVING PROCESS
Plate Recivied At Shop
Plates Unloading
After Materail recivied check as per challan (Size & QTY.)
Check Challan As per PO
As Per Challan Fill up the GRN
Recored & Check the HEAT NUMBER ,PLATE NUMBER Afetr Give To QC DEPT.
Matrail Size Give To Design DEPT.
Layout Taken from Design DEPT.
PARALLEL ACTIVITY | BAFFLE MAKING | TUBESHEET MAKING | BELLOW MAKING | HEADER RHS /LHS | DISHEND MAKING | BODY FLANGE | SHELL MAKING | PIPE TO FLANGE FITUP | LIFITING LUG MAKING | RF PAD
BAFFLE MAKING | Baffle Plate Marking / Cutting | Plate Marking | Plate Marking | Shell Plate Marking | Plate Marking | Plate Cutting | Shell Plate Marking | Pipe Cutting | Marking | Marking
TUBESHEET MAKING | Drilling | Plate Cutting | Cutting | Shell Plate Cutting | Cutting | Segment Bevelling Or Plate Bending | Shell Plate Cutting | Pipe Bevelling | Cutting | Cutting
DISHEND MAKING | Machining | Machining | To Vendor | Shell Plate Pre Punching | To Vendor | Segment Fitup | Plate Bevelling | Pipe To Flange Setup | Setup | Grinding
BODY FLANGE | Tie Rod Spacer Cutting | Hole Marking | Bending | Plate Rolling | Bending | Body Flange segment welding | Pre-punching | Welding | Welding
SHELL MAKING | Skeltan Making | Drilling | From Vendor | L-Seam Setup | Inspection At Vendor End | Straightening | Rolling | RT (IF REQUIRED) | Grinding/Finishing
PIPE TO FLANGE FITUP | Bunddle Making | Slot Marking | Inside ID cutting | L-Seam Welding | From Vendor | Grinding/Finishing | L-Seam Fitup
LIFITING LUG MAKING | Fitup external plate fitup on bundle(if given in drawing) | Grooving | To Vendor | Re-Rolling | Ready Dishend Received At Shop | RT/UT (IF REQUIRED) | Plate L-seam welding
RF PAD | welding |  | Bending | Shell To Dish/Body Flange fitup | Dish Bevelling | Machining | Inside Grinding/Finishing
BELLOW | finishing |  | Ready Bellow Received At Shop | welding |  | Drilling | Re-Rolling
HEADER |  |  | Bellow Bevelling | Nozzle marking & cutting |  | Liner Fitup (IF REQUIRED)
|  |  |  | Nozzle setup |  | Liner Welding
|  |  |  | Nozzle welding |  | Machining
Fabrication Activity
C-seam Fitup (Shell Or Bellow)
Welding
Inside Grinding/Finishing
Nozzle marking
Profile Cutting/Grinding
Nozzle Fitup
Nozzle welding
Inside Back-chip Grinding
Internals Fitup (Partition plate,Vapour box,etc.)
Internal Welding
Skeleton making
Bundle making
Tube insert
Bundle insert
Tubesheet Fitup
welding
Tube guide
tube welding
Tube Expansion
Outside Fitup
Welding
Finishing
Shell side Pneumtic Test
Shell Hydro Test
Tube side Pneumtic Test
Tube Hydro
Painting
Dispatch

## HE REBOILER
REBOILER
MATERAIL RECEIVING PROCESS
Plate Recivied At Shop
Plates Unloading
After Materail recivied check as per challan (Size & QTY.)
Check Challan As per PO
As Per Challan Fill up the GRN
Recored & Check the HEAT NUMBER ,PLATE NUMBER Afetr Give To QC DEPT.
Matrail Size Give To Design DEPT.
Layout Taken from Design DEPT.
PARALLEL ACTIVITY | BAFFLE MAKING | TUBESHEET MAKING | CONE MAKING | HEADER RHS /LHS | CONE MAKING | DISHEND MAKING | BODY FLANGE | SHELL MAKING | PIPE TO FLANGE FITUP | LIFITING LUG MAKING | RF PAD | N1 Nozzle
BAFFLE MAKING | Baffle Plate Marking / Cutting | Plate Marking | Plate Marking | Shell Plate Marking | Plate Marking | Plate Marking | Plate Cutting | Shell Plate Marking | Pipe Cutting | Marking | Marking | Sheel to cone setup
TUBESHEET MAKING | Drilling | Plate Cutting | Cutting | Shell Plate Cutting | Cutting | Cutting | Segment Bevelling Or Plate Bending | Shell Plate Cutting | Pipe Bevelling | Cutting | Cutting | welding
DISHEND MAKING | Machining | Machining | To Vendor | Shell Plate Pre Punching | To Vendor | To Vendor | Segment Fitup | Plate Bevelling | Pipe To Flange Setup | Setup | Grinding | cone to shell setup
BODY FLANGE | Tie Rod Spacer Cutting | Hole Marking | Bending | Plate Rolling | Bending | Bending | Body Flange segment welding | Pre-punching | Welding | Welding |  | welding
SHELL MAKING | Skeltan Making | Drilling | Inspection At Vendor End | L-Seam Setup | Inspection At Vendor End | Inspection At Vendor End | Straightening | Rolling | RT (IF REQUIRED) | Grinding/Finishing |  | body flange setup
PIPE TO FLANGE FITUP | Bunddle Making | Slot Marking | From Vendor | L-Seam Welding | From Vendor | From Vendor | Grinding/Finishing | L-Seam Fitup |  |  |  | welding
LIFITING LUG MAKING | Fitup external plate fitup on bundle(if given in drawing) | Grooving | Ready Cone Received At Shop | Re-Rolling | Ready Cone Received At Shop | Ready Dishend Received At Shop | RT/UT (IF REQUIRED) | Plate L-seam welding |  |  |  | nozzle marking
RF PAD | welding |  | L Seam Welding | Shell To Dish/Body Flange fitup | L Seam Welding | Dish Bevelling | Machining | Inside Grinding/Finishing |  |  |  | cutting & v prepraction
BELLOW | finishing |  | inside grinding | welding | inside grinding |  | Drilling | Re-Rolling |  |  |  | nozzle setup
HEADER |  |  | RT | Nozzle marking & cutting | RT |  | Liner Fitup (IF REQUIRED) |  |  |  |  | welding
CONE |  |  | Cone Bevelling | Nozzle setup | Cone Bevelling |  | Liner Welding |  |  |  |  | inside grinding
|  |  |  | Nozzle welding |  |  | Machining |  |  |  |  | welding
|  |  |  | Finishing | [7 empty] | finishing
Fabrication Activity
C-seam Fitup
Welding
Inside Grinding/Finishing
Shell to cone setup
welding
Nozzle marking
Profile Cutting/Grinding
Nozzle Fitup
Nozzle welding
Inside Back-chip Grinding
Internals Fitup (Partition plate,Vapour box,etc.)
Internal Welding
Skeleton making
Bundle making
Tube insert
Bundle insert
Tubesheet Fitup
welding
Tube guide
tube welding
Tube Expansion
Outside Fitup
Welding
Finishing
Shell side Pneumtic Test
Shell Hydro Test
Tube side Pneumtic Test
Tube Hydro
Painting
Dispatch