## Slide 1: Production & Planning Control
Organizational Requirements

## Slide 2: 1. Input Provisions

## Slide 3: 1.1 List of Employees
SR. NO. | NAME | DEPARTMENT | EXPERTISE IN SKILLS | RESPONSIBILITIES

## Slide 4: 1.2 Department wise List of Skills
1.2.1 Design Department
Design Calculations (CADEM)
AutoCAD Drafting
Solid Edge 3D Modelling
Solid Edge Drafting
Most 2D work

## Slide 5: 1.2 Department wise List of Skills
1.2.2 Production Department
Welder
Fitter
Tacker
Machinist
Helper

## Slide 6: 1.2 Department wise List of Skills
1.2.3 Quality Department
RT film interpretation
TC Validation
POS Validation
Inspection (Measurements)
Documentation

## Slide 7: 1.2 Department wise List of Skills
1.2.4 Other Skills
Shot Blaster
Painter
Packer
Job loader
Job Unloader

## Slide 8: 1.3 List of Activities with required skill person
Dept | Activity | Skill Required-I | Quantity | Skills Required-II | Quantity | Time required
Design | Fabrication drawing | AutoCAD Darting | 2 | NA | 0 | 16 Hours
Production | Seam welding | Welder | 1 | Helper | 2 | 8 Hours

## Slide 9: 1.4 In process Inspection Stages
Facility should be provided to insert the in process inspection stages before or after Production Stages.
1.5 Defining interdependencies of processes
Provision to be there for defining Interdependencies of activities or group of activities.

## Slide 10: 1.6 Provision to enter start time of specific activity
Facility should be provided to enter start time of specific activity.
Once the project start date given to software, Job completion date should be generate automatically based on time defined for each activity and available resources.
If situation occurs to define start date of process manually, that facility should provided, which will helpful to track actual delayed activities. E.g. If purchased Item delivery is late and this delay can not be considered as organizational delay.

## Slide 11: 2. Project windows

## Slide 12: 2.1 First Window
Add New Project
Edit Project
View Results Project wise
View overall results
Equi. Type
Tank
HE
Colum
List of Project
List of Projects
Open Combine Project window
Project Data Window, Proj Name, no, client, spef etc
Open Project Window
Open project window
Enter/Edit Parameters
View required results
Start Project
View required results
Update
Organizational data
List of Employees
List of Skills
Slandered List of Activities

## Slide 13: 2.2 New Project Data Window
Project No:
Type of Equipment:
PO Date:
Del. date:
Quantity:
TAG No:
Description
Add Project
Reset Project

## Slide 14: 2.3 Project Window
Project No:
PO Date:
Start date:
Target Completion date:
Percentage completion:
Current Early/Delay status:
Design
Production
Quality
Purchase Dept
Planning
View Results

## Slide 15: 2.4 Design Department window
Act. No. | Activity | Skills I | Manpower Req. | Name of person | Skills II | Manpower Req. | Name of person | Time Required | Start Date | Target Date | Completion Date | Client Approval | Release Date | Revision No | Delay | Reason
D1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
D2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
To be filled by Production planner One time /will come automatically
To be filled by Supervisor
To be filed by departmental head
Automatically Calculated

## Slide 16: 2.5 Purchase Department window
SR.NO | Description | Material Specification | Size | Qty | Available Stock | To be Procured | Target Date | PO Released Date | Expected Del Date | Actual Rec. date | Material TC required | TC Received
BOM should be updated by uploading excel file, copy paste excel sheet.

## Slide 17: 2.6 Production Department window
Act. No. | Activity | Skills I | Qty | Name of person | Skills II | Qty | Name of person | Material Required (from BOM) | Time Required | Start Date | Target Date | Completion Date | Approval | Release Date | Delay Days | Reason
P01 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
P02 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
To be filled by Production planner One time /will come automatically
To be filled by Supervisor
To be filed by departmental head
Automatically Calculated

## Slide 18: 2.7 Qulity Department window
RADIOGRAPHY |  |  |  |  | 
JOB NO | RT OFFER | RESULT | REMARk |  | 
PRE-DISPATCH |  |  |  |  | 
JOB NO | Actual | Inspection By production | Inspection by QC | Spare list | Transport saddle
DOSSIER |  |  |  |  | 
JOB NO | Planned | Actual |  |  | 

## Slide 19: 3. Project Reports

## Slide 20: 3.1 Project status report
Timely weighed percentage completion of the report.
Time required to completion of project considering current delay.
Department wise percentage completion of Activities.

## Slide 21: 3.2 Project Health report
Are we able to deliver the project on targeted time? (comment). Are we stagnated?
Total Delay.
List of delayed activities.

## Slide 22: 3.3 Team Availability Report
Availability report of person with name, for at least next 1 Month.
Skill wise Availability report of person
Person wise work Load

## Slide 23: 3.4 Risk Report
List of major obstacles for achieving targets, from past data of projects and their current status.
List of obstacles which may manually entered.

## Slide 24: 3.5 Variance Report
Overall Variance observed in Time
Activity wise Variance observed in Time

## Slide 25: 3.6 Time Tracking Report
Person wise time tracking for completion of activity